## Sheet1
Number	Tasks	Status	Pirority	Estimate	Assigned To:
1	set up the repository	DONE	HIGH	1 HR

2	connect team members to repository	DONE	HIGH	1 HR

3	make sure code editor is working and connected to repository	DONE	HIGH	1 HR

4	make sure sql is up and running on team members machines	In-Progress	HIGH	2 HRS

5	create user stories and acceptance criteria	DONE	HIGH	5 HRS

6	review user stories	DONE	HIGH	2 HRS

7	organise repository / folders/ correct names of folders	In-Progress	MEDIUM	2 HRS	Padraig

8	create test design	In-Progress	HIGH	2 HRS	Liam

9	create diagrams for code classes	In-Progress	HIGH	3 HRS	Michael

10	create diagrams for sql database	In-Progress	MEDIUM	2 HRS	Ben

11	make tables for database	TO-DO	HIGH	3 HRS

12	connect sql to java	TO-DO	MEDIUM	2HRS

13