## Sheet1
Number	Tasks	Status	Pirority	Estimate	Assigned To:
1	set up the repository	DONE	HIGH	1 HR	Michael

2	connect team members to repository	DONE	HIGH	1 HR	Team

3	make sure code editor is working and connected to repository	DONE	HIGH	1 HR	Ben

4	make sure sql is up and running on team members machines	DONE	HIGH	2 HRS	Team

5	create user stories and acceptance criteria	DONE	HIGH	5 HRS	Team

6	review user stories	DONE	HIGH	2 HRS	Team

7	organise repository / folders/ correct names of folders	DONE	MEDIUM	2 HRS	Padraig

8	create test design	DONE	HIGH	2 HRS	Liam

9	create diagrams for code classes	DONE	HIGH	3 HRS	Michael

10	create diagrams for sql database	DONE	MEDIUM	2 HRS	Ben

11	make tables for database	DONE	HIGH	3 HRS	Ben

12	connect sql to java	DONE	MEDIUM	2HRS	Team

13	Create Customer class	DONE	HIGH	1 HR	Padraig

14	Create Publications Class	DONE	HIGH	2 HRS	Liam

15	Create Invoice Class	DONE	HIGH	1HR	Liam

16	Create Deliveries Class	DONE	HIGH	1HR	Liam

17	Create Order Class	DONE	HIGH	1HR	Michael

18	Create Junit Tests	DONE	HIGH	1HR	Team

19	Create Java Skeleton Code	DONE	HIGH	1HR	Team

20	Sprint Review	TO-DO	LOW	3HRS	Team

21	Read Customer class	TO-DO	HIGH	3HRS	Padraig

22	Read Order class	TO-DO	HIGH	3HRS	Michael

23	Read Invoice class	TO-DO	HIGH	3HRS	Liam

24	Read Publications class	TO-DO	HIGH	3HRS	Ben

25	Read Deliveries class	TO-DO	HIGH	3HRS	Liam